## Gap Analysis
# | Category | Gap Identified | Clarification Required | Key Questions to be Answered | Owner (to respond) | EXL Draft Response
1 | Security / SOX | Certificate segregation is implied but not explicit | Explicit confirmation of a dedicated third Eclipse certificate set for Xtrakto.AI | • Will Xtrakto.AI use a dedicated certificate set separate from Opus and Lighthouse? • How will certificates be rotated, revoked and segregated by environment? | EXL/Bruce to get these issued. Confirmed that new set of certificates will be needed. Need to ensure that EXL have a support process to ensure certificates are managed appropriately. | • Dedicated PFX certificate issued by Eclipse for Xtrakto.AI — stored in AWS Secrets Manager • Need details on frequency of certificate rotation from BRIT • Rotation mechanism and ownership to be added to Support & Maintenance runbook
2 | Security / SOX | System-based segregation of duties (SoD) not documented | Make SoD assumptions explicit for automation | • How is SoD satisfied when the "actor" is a system? • What logs provide full attribution for audit review? | EXL to provide the answers in design. | • Awaiting input from BRIT and Verisk on whether permissions can be locked at certificate level
3 | Performance | 50 concurrent requests/min appears assumption-based | Evidence-based justification or adjustment | • What is the expected peak concurrency model? • Why was 50 concurrent requests/min chosen? Can Verisk share if this version of Eclipse can deal with that load? • Has this been workload-modelled or stress-tested on BRIT's eclipse instance? | EXL | • Based on past experience — Eclipse API is called only after user validates information on screen (human-in-the-loop) • Given the manual trigger, load exceeding 50 concurrent requests/min is not anticipated • Verisk confirmed no configurable concurrency parameter exists on their side • Load validation to be covered as part of unit testing — guidance to be sought from Verisk prior to execution
4 | Performance | 20-second SLA lacks clear rationale | Confirm whether SLA is hard or indicative | • Why was 20 seconds chosen? • Is this an acceptance criterion or best-endeavours target? | EXL / Xtrakto.AI (input from Verisk helpful) | • 20-second SLA is based on expected Eclipse API response time plus Xtrakto.AI processing overhead • Currently indicative — BRIT/EXL to confirm if this is a hard acceptance criterion or best-endeavours target
5 | Data Consistency | No explicit transaction / compensation handling | Define behaviour for partial failures | • Are multiple Eclipse APIs used per transaction? • What happens if step 2 fails after step 1 succeeds? | EXL / Xtrakto.AI to produce as part of the solution design, failure scenarios and the expected behaviour on xtracto.ai side. | • Eclipse API is called for each successfully validated transaction on the UI • A case is marked complete only if all Eclipse updates are successful • Any failure at any point surfaces an error on screen — human to handle that case outside of Xtrakto.AI
6 | Data Integrity | Deduplication scope not precise | Explicitly define idempotency keys | • What identifier(s) are used for deduplication? • How long is the deduplication window maintained? | EXL | • Awaiting further clarification — to be discussed
7 | Error Handling | Ownership after retries exhausted unclear | Define failure ownership & escalation | • Who owns investigation after retries fail? • When is Eclipse/Verisk engaged vs handled internally? | EXL / Xtrakto.AI + BRIT IT Ops – Need to agree the support model for error handling as this is a SOX application. | • Any Eclipse API failure is surfaced immediately on screen to the user • User is responsible for handling the failed case outside of Xtrakto.AI • No automated retry — human-in-the-loop acts as the error handling mechanism
8 | Support / Operating Model | End-to-end support model not agreed | Operating model definition required | • How do incidents enter BRIT ITSM? • Who provides first- and second-line support? | BRIT IT Ops (with EXL input) and agreement with the sponsors | • Need clarity on what types of support/incidents are being discussed before a response can be provided
9 | Observability | No health checks or proactive alerting defined | Add health monitoring expectations | • Are health endpoints provided? • What alerts exist for queue build-up / Eclipse downtime? | EXL to confirm this is in scope. Please add to the NFRs. | • To be discussed
10 | Audit / Compliance | Evidence mechanism not specified | Define audit evidence & access | • How can BRIT access logs on request? • What evidence is provided pre-go-live for SOX controls? | EXL to confirm this is in scope. Please add to the NFRS. | • Logs will be stored for every request made to Eclipse, linked to the transaction ID and associated case • Data retention period to align with what is declared in the SLA • Log file for any specific case can be shared on request as audit evidence
11 | Audit / Compliance | Log retention period unspecified | Define retention and retrieval SLAs | • How long are logs retained? (SOX expectation ~7 years) • Retrieval SLA for audit requests? | EXL to confirm this is in scope. Please add to the NFRS. | • Logs will be stored for every request made to Eclipse, linked to the transaction ID and associated case • Data retention period to align with what is declared in the SLA • Log file for any specific case can be shared on request as audit evidence
12 | Acceptance / Assurance | NFRs define intent but not proof | Define acceptance criteria per Critical NFR | • What evidence proves each Critical NFR is met? • Which items can be explicitly waived by the app owner? | App Owner – Keith and Bruce to verify what verification and evidence needs to be provided to EXL before this change can go live. | EXL will produce a traceability matrix mapping each Critical NFR to a measurable acceptance criterion and evidence type (e.g., load test report, penetration test certificate, log sample, SLA dashboard screenshot). Items proposed for waiver by the App Owner (Keith/Bruce) will be flagged explicitly with a risk-accepted rationale. EXL requests that Keith and Bruce confirm the waiver process and any required sign-off format before the go-live gate review.